## Project Planner
Sprint 3 - Agility
Select a period to highlight at right. A legend describing the charting follows. | [5 empty] | Period Highlight: |  |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | STAFF MEMBER(S) | PLAN START (Hours) | PLAN DURATION (Hours) | ACTUAL START (Hours) | ACTUAL DURATION (Hours) | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Planning Phase | All Members | 1 | 1 | 1 | 2 | 100%
Gantt Chart | Zak | 2 | 1 | 2 | 2 | 100%
Requirements Table | Vincent | 2 | 2 | 2 | 2.5 | 100%
Flowchart | Zak | 4 | 1 | 4 | 1 | 100%
Algorithm | Mason | 4 | 1 | 4 | 1 | 100%
Movement Code | Vincent | 4 | 2 | 4 | 3 | 100%
Testing for Expected Result | All Members | 6 | 2 | 6 | 3 | 100%
Debugging | Vincent | 7 | 2 | 7 | 2 | 100%
SDD Sheet | All Members | 9 | 1 | 9 | 1 | 100%
Video Recorded | All Members | 9 | 1 | 9 | 1 | 100%
Upload to Github | All Members | 10 | 1 | 10 | 1 | 100%
Activity 12 | [5 empty] | 100%
Activity 13 | [5 empty] | 0%
Activity 14 | [5 empty] | 0%
Activity 15 | [5 empty] | 0%
Activity 16 | [5 empty] | 0%
Activity 17 | [5 empty] | 0%
Activity 18 | [5 empty] | 0%
Activity 19 | [5 empty] | 0%
Activity 20 | [5 empty] | 0%
Activity 21 | [5 empty] | 0%
Activity 22 | [5 empty] | 0%
Activity 23 | [5 empty] | 0%
Activity 24 | [5 empty] | 0%
Activity 25 | [5 empty] | 0%
Activity 26 | [5 empty] | 0%